## Sheet1
Id | Date | Activity Summary
1 | 2025-01-29 15:53 | I set up the log book to document work throughout the process. I also started filling out the project safety plan document and started formatting the preliminary report
2 | 2025-01-30 16:30 | Worked on the preliminary report, made a basic draft of the introduction and objectives. Started work on the ethics section and started looking for sources and papers to learn more about the topic and to seek out other models in which to validate my future work against.
3 | 2025-02-04 18:14 | Researched more ethical topics to discuss in the ethics section of the
4 | 2025-02-06 21:59 | Expanded on introduction and goals for the preliminary report The ethics section was also expanded and subdivide into 3 sections. (researcher, engineer and member of society) the engineer ethics was expanded the most
5 | 2025-02-11 14:21 | This Log is to log work that was done over the past week that I neglected to Log. The project safety plan was completed and submitted The preliminary report was completed, In it I outlined Objectives and a path research as well as a schedule This log will also mark the logs becoming more structured, with a work plan being logged at the days start and a work acknowledgment being logged at the days end
6 | 2025-02-12 14:53 | Work Plan: - Fix mistakes and issues with prelim report to prepare it for the project report - Get access to Science Direct for research papers
7 | 2025-02-18 12:25 | This Entry is a summary of work over the last week until now. Work has been done to take the preliminary report and to take its contents and use it to create the project report, in doing so the following changes were made. - The Research Section was restructured to include heading and subheading that reflect the research objectives set out in the objectives section of the document - The Work Plan was expanded to have a Gannt chart and a table that breaks it down in more detail. - The references section was reformatted, but going forward I will by trying to use MS words in built system for referencing Plans for the next week: - start formatting the appendices as there are a number of things that need to be added in to an appendix - Read more papers so that solartracking methods can be identified
8 | 2025-02-19 13:18 | as outlined in the last entry more papers need to be identified to identify methods of solar tracking, Ill be placing particular focus on looking at the position control aspect of the solar tracking method. The aim is to get at least 3 resources for each sub headings under RO1 The next log entry should mention the resources found by days end
9 | 2025-02-19 16:52 | I found a few papers that look promising as they all specifically mention the domestic use of the tracking system. https://ieeexplore-ieee-org.tudublin.idm.oclc.org/stamp/stamp.jsp?tp=&arnumber=9687778 The first paper of interest is an IEEE paper, it outlines a number of parameters that effect performance as well as how to handle these parameters https://ieeexplore.ieee.org/abstract/document/10534410/figures#figures Another IEE paper, this paper looks at designing optimal parameters for a single-axis Solar tracker, it utilises a PD controller https://www.sciencedirect.com/science/article/pii/S0360544223033832 This paper found on science direct is more focused on performance improvement, one method being setting delay times to reduce the energy use of the tracking system. As I am currently focused on solar tracking methods I will shelf this paper for now but will come back to it when looking at control strategies for performance improvement. https://jurnal.iicet.org/index.php/sajts/article/view/4448 This paper looks at designing a domestic system that rotates 60 degrees east to west using an LDR sensor set up https://ijmer.s3.amazonaws.com/pdf/volume11/volume11-issue8(6)/13.pdf This paper looks at using A HMI and PLC to make a time based solar tracking system all these papers will need to be examined further
10 | 2025-02-25 17:14 | The attached papers were read and marked, to determine the parts that will be used for the lit review. There is still work do to on some of the papers and I need to compare and contrast the outlooks of the papers. The Current take aways from reading the papers thus far is as follows - single-axis and dual-axis both out perform fix installations of PV panels. - single-axis is popular as is the middle ground between cost and efficiency making is the more economical option. - the best mechanism for moving the PV panel depends of multiple parameters such as global location and weather conditions. The goal for tomorrows work is to be able finish off the analysis of the papers to be able to begin the synthesis of the lit review, but also potentially it may be worth looking for more papers, as there isn't a lot of resources that focus particularly on the domestic use of solar panels. Tomorrow I will have a meeting with my supervisor to discuss my findings thus far and to see what other steps may be necessary.
11 | 2025-03-04 12:40 | This week I seek to get a working simulation model of solar tracking. I was reading a paper that had a model built out in simulink but the paper was not 100% transparent about their methods, so it would be difficult to try and re create the model. I had also found a MATLAB file share with a model that compares tracking to static PV panels, but I have been experiencing trouble with the model as I believe that the model is missing files. I resource will still be helpful to use as a base to create a model but it does mean I can use this model to validate results against. I may need to find more potential models for validation down the line. So assure the modelling goes well I am going to do the simscape on ramp to gain a better understanding of its use in building models. Additionally I aim to make progress in writing a intro and lit review for the project document
12 | 2025-03-04 16:38 | Todays worked achieved includes - Completion of Simulinks simscape on ramp - Identification of additional solar tracking models that may be suitable for validation - Further research for Lit review done While Im not completely happy with the amount of work achieved today, I am happy that I am now better equipped for building models in future. In an effort to ramp up work, I seek to Write in the Lit review and intro for the project document, as well as start the build of the model all by days end tomorrow. The plan is to first complete the lit review so that I can justify even to myself my methodology before doing the simulations and model building. Based on the project meeting earlier this week, I find it important to highlight the importance to simply measure the performance of adding in solar tracking, rather that the performance of a single specific tracking algorithm, but I willing to see how an algorithm may be implemented into the model itself. Finally I just wanted to write about what I feel the current scope of the project is. In my research thus far, few papers look at the use of solar tracking in a domestic or residential area. I believe that making PV more efficient for home owners could potentially increase the likely hood of people installing PV in their homes. This means for my project as it currently stands, factors I consider important is as follows - cost, such as initial investment, maintained or pay back period - scalability, how Widley can it be applied with minimal changes or at least with easy adjustments - Form, does the technology physical conform to the needs or constraints of a house
13 | 2025-03-06 18:25 | It has been difficult to find a model of simulation that works as many models use simscape multibody a tool not available to me. additionally it has been very trouble some to get the data I need for simulation. I believe that after a long day of searching I have found an appropriate data set, it will be a bit of a slow set up to use it but the quality of the data seems good. I think I should be able to go to get a good amount of the model made this weekend if all goes well. Over all I believe that the project has legs but I do feel a little bit behind where I should be, but looking at my project plan I still have another week or so, to have another working model. I just need to make sure that model I do make is able to be validated.
14 | 2025-03-20 17:12 | Work Update - This entry is going to go over the work I've cover since the last entry. These past two weeks I have been focused on making the model for the project. In this time I researched many papers and now have a clearer understanding of the methods used for these solar tracking models. I have since resolved data issues, as I not have appropriate data The solar tracking algorithm has been the main focus of this week, in my research it seem that it would be easiest to implement an astrology based algorithm rather than a sensor array as simulating sensors would involve some aspect of synthesising data where as the astrology method would allow for the use real data to be plugged straight into the model. In terms of the astrology method I've found there to be two methods broadly speaking, while both methods use a mathematical model to know where the sun is going to be, there's one form of modelling that goers further with the mathematical model using equations to estimate sun light over a few months and then there's the other method that is focused on simulating the mechanical aspects of the solar tracking, given that my project is more focused on the use of simulation rather than the analysis of the of solar tracking I am focused on the more mechanical simulation. I have found a model that uses a worm and gear constraint to move the panel, the plan would be to use a different rotation mechanism if I can. The work that I hope to finish this week is my discussion of the model building techniques and to have the simulation up and running. this would enable me to start a deeper dive into control methodologies that could improve the system, such as adjusting the rotation mechanism, or using cascade control to speed up tracking speed or potentially using timers to reduce on time to reduce energy consumption.
15 | 2025-03-26 10:26 | Work Update I finished the parts of the lit review I wanted to write and began my experimentation with the Simulink model I found. the plan is to strip it back to a more simplified model and then build it up with the control strategies I explore, I'll have to ensure that I keep good version control of it so that I dont lose anything important and that I can effectively show how I made the simulation my own
16 | 2025-03-27 14:08 | The Plan for the Simulation is to break it down in more detail to be able to access what it does well and what needs changing. A very basic example of this is that the simulation utilizes an ANN so ill have to see if I can get it working without it as its trained on a specific data set so I need to ensure that the sim will still work with my data set. That being said I will attempt to try and introduce some of these control strategies later when investigating control strategy methods On another note, I will attach the data I plan on using, as well as the found simulations data, to maintain transparency The SolarData xlsx is my data, and the combined_solar_irradiance_data_1 xlsx if from the github project
17 | 2025-03-27 18:50 | Today I ran the sim with some signals being data logged. The main reason for doing this was so see how the signals behave, to get a better idea of the inner workings (the data log file format is not supported by MS Forms and neither is a zip file so it cant be attached) In looking for signals that would be appropriate for data logging, I gained a much more indebt understanding of the inner workings of the sim. The ANN seems to be trained on data from multiple countries, so it may actually be usable for the project. I will investigate this further. The Sim is broken down into two parts one being the movement of the actual panel (the position control system) and then the power generation side of it. The main thing I would like to adjust with the sim over the next bit is - Remove the additional panel as I believe I would only need 1 - Adjust the mechanical movement of the panel - Introduce a static panel to have a comparison - I may remove the MPPT as its not relevant to the project - again I may remove the battery charging aspect of the sim as its not under the scope of the project
18 | 2025-04-01 16:15 | So far I've taken many steps to understand and dissect the simulation. I've made some small adjustments and started a folder to maintain version control so that I have a history of changes made. I've placed many comments around the simulink to have a visual aid of what needs to be done For now the focus is getting in a static panel for the results comparison and being able to use my own data set. The main barrier to me currently is the overwhelming nature of the amount of task set in front of me, but that's where organising the work comes in handy, being able to see how each small piece of work will eventually fit together helps to make the amount of work fell less daunting. Additionally I do lack some knowledge on simscape multibody but that should be possible to fix with additional on ramps and there is still plenty of other work that I can still do without an indebt knowledge of multibody
19 | 2025-04-03 15:03 | So far this week I have been working on adding in functionality to allow for a static and tracking panel comparison. The main hurdle I've been attempting to overcome is scaling the irradiance data to reflect the difference in alignment between the solar vector and the panel normal vector. I spent a good amount of time deriving the equations to do so, and given the amount of time it took to do I should add this to the final report to show the work that was done. While I mathematically proved it can be done it does still leave a lot of work to be done in terms of implementation. So currently I am working on a system that takes the two vectors and does the math to determine the cosine of the angle of incidence, but doing so has highlighted other issues I need to tackle such as how I orient the static panel, while I could do it random it would make for a bad faith argument when comparing static vs tracking. So I need to read further on algorithms used to find the ideal orientation of a static panel given longitude and latitude. While this subsystem does come with these many issue I believe that the pursuit is worth while as it eliminates some assumptions the previous simulation made. Additionally I can use this subsystem for the tracking panel too, I'm planning on making the subsystem actually dynamically see where the position control system currently is as simulated using multibody. As of this log, I am working on version 3 of the simulation.
20 | 2025-04-13 15:34 | As of writing this I am working on version 7 and shorty going to move onto version 8. The Simulation runs but there are some changes I would like to make such as changing the tracking mechanism to single axis. Additional I need to add other elements such as integrators to get an over all power generation comparison for the static vs tracking I am now also running into and issue with the sun azimuth position is being calculated, as the azimuth is calculated with respect to the compass it mean that in my data set the azimuth crosses 0 over to 360 degrees, by itself its fine but the issue arrived when I'm comparing the azimuth to thee panel azimuth which starts at 0, so I need to see how to adjust that for the panel azimuth. So over all I am happy the simulation is in a working state but I would like to make some more changes before I write it up in documentation. So the hope if that over the easter break the first week will be a wrap up of simulation with some documentation writing and the second week will comprise solely of documentation writing.
21 | 2025-04-19 19:30 | I've found a way to solve the azimuth issue, the problem itself arose from the sun positioning algorithm using south as the reference for azimuth where I needed it to be north based, I was able to offset the reference by just adding 180 and using MATLABs mod() function to clamp the value between and 360. I added in integrators to get the area under the curves, they're quite small but I think the value will still work for comparison to see the added benefit for the tracker. I still need to change the tracking mechanism to single axis, so for that I'll need to brush up on my understanding of simscape multibody. I plan on doing the on ramp to assist in this.
22 | 2025-04-26 20:40 | I has some trouble learning multibody but I learned enough to be able to change the rotation mechanism to a tilted vertical single axis tracker, I would have preferred to do a polar tilted single axis tracker but given time constraints I'll have to include that in the future work. I finally have a working simulation I am happy with now and I am able to graph results, I'll be focusing on writing the documentation for the project for the next week or so.
23 | 2025-05-21 11:56 | After Exams, I added in a energy consumption minimisation technique as well as a method to change the location of the system using an ANN, this would allow me to test the system in other countries, I chose a few countries based on diversity in coordinates and diversity in the weather. I did use AI to help me choose location so I wouldn't be biased towards European countries, I felt like I ended up with a diverse range which make the testing more interesting and robust. I also set up the git hub for the project so I can have honest and transparency for the project